## Epic for Clinical research anal
Epic | User Story ID | User Story Title | Component | Developer Task | UI Objects on Screen | Story Points | Dependencies | Priority | Sprint | Acceptance Criteria | Testing Details
Epic 1: Data Ingestion & Management | US1 | FE: Clinical Trials Search Criteria Input | Frontend | Develop React form to accept search criteria for clinical trials data (e.g., drug name, medical condition, trial status) | Search bar, filter options (dropdowns, checkboxes), date pickers, submit button | 5 | US12 | High | 1 | - Functionality matches the business requirement for accepting user-defined search criteria. - User input is validated before submission. - The UI is responsive and provides a clear user experience. - The search criteria are successfully passed to the backend API. | Unit Tests: Test form validation and state management.Integration Tests: Verify that the form correctly sends data to the backend endpoint.UI/UX Testing: Ensure the form is intuitive and accessible on different devices.UAT: Confirm a user can successfully enter criteria and initiate a search.
Epic 1: Data Ingestion & Management | US2 | BE: Extract Clinical Trials Data | Backend | Develop API endpoint and web scraping logic to extract data from clinicaltrials.gov based on frontend criteria | N/A | 8 | US1 | High | 1 | - The API receives search criteria from the frontend. - Data is extracted from clinicaltrials.gov based on the received criteria. - Structured data is saved correctly into PostgreSQL. - Relevant unstructured text data is saved correctly into the vector database. - The API responds with a status code indicating success or failure. | Unit Tests: Test data extraction logic for various criteria and edge cases.Integration Tests: Verify end-to-end data flow from the API call to data storage.API Testing: Verify request/response formats, status codes, and error handling for the ingestion API.
Epic 1: Data Ingestion & Management | US3 | FE: Display Clinical Trials Data | Frontend | Develop React dashboard to display clinical trial data retrieved from the local database based on user criteria | Search bar, filter options, result cards/tables, charts (bar, line, pie), data export buttons (CSV, PDF), pagination | 8 | US2 | High | 2 | - Functionality matches the business requirement for displaying clinical trial data. - Results are presented clearly and concisely. - The UI is responsive and consistent with design guidelines. - All UI objects listed are present and functional. - Data is correctly retrieved from the local database. | Unit Tests: Test data rendering in various chart types and tables.Integration Tests: Verify data flow from the local database to the frontend display.UI/UX Testing: Verify presence of all UI objects and interactions; test responsiveness on multiple screen sizes.UAT: Confirm the user can view, filter, and export the clinical trial data.
Epic 1: Data Ingestion & Management | US4 | Ingest Financial Filings (10-K) | Backend | Implement SEC.gov API integration and document parsing | N/A | 8 | US12 | High | 2 | - Functionality matches the business requirement for ingesting Form 10-K data from SEC.gov. - No errors during API calls and document parsing. - Extracted textual data is saved correctly into the vector database. - Structured metadata (e.g., filing date, company) is saved correctly into PostgreSQL. - APIs respond within acceptable latency and return correct status codes. | Unit Tests: Test parsing logic for different 10-K formats and edge cases.Integration Tests: Verify end-to-end data flow from SEC.gov to PostgreSQL and Vector DB.API Testing (Backend only): Verify request/response formats, status codes, and error handling for the ingestion API.UAT: Confirm data ingestion meets user needs and acceptance criteria.
Epic 1: Data Ingestion & Management | US5 | Ingest Scientific Papers | Backend | Develop web scraping for Google Scholar and other scientific databases | N/A | 8 | US12 | High | 3 | - Functionality matches the business requirement for ingesting scientific papers. - No errors during scraping and text extraction. - Full-text content is saved correctly into the vector database. - Metadata (e.g., author, journal, publication date) is saved correctly into PostgreSQL. - APIs respond within acceptable latency and return correct status codes. | Unit Tests: Test text extraction from various document formats (PDF, HTML).Integration Tests: Verify end-to-end data flow from source to PostgreSQL and Vector DB.API Testing (Backend only): Verify request/response formats, status codes, and error handling.UAT: Confirm data ingestion meets user needs and acceptance criteria.
Epic 1: Data Ingestion & Management | US6 | Ingest Media Releases | Backend | Implement web scraping for company public sites. Eg. use News API to get media releases. | N/A | 5 | US12 | Medium | 3 | - Functionality matches the business requirement for ingesting media releases. - No errors during scraping and text extraction. - Textual content is saved correctly into the vector database. - Metadata (e.g., publication date, source) is saved correctly into PostgreSQL. - APIs respond within acceptable latency and return correct status codes. | Unit Tests: Test content extraction from various news website structures.Integration Tests: Verify end-to-end data flow from source to PostgreSQL and Vector DB.API Testing (Backend only): Verify request/response formats, status codes, and error handling.UAT: Confirm data ingestion meets user needs and acceptance criteria.
Epic 2: AI-Powered Research Analysis Engine | US7 | Medical Condition Analysis | Backend | Develop LangChain/LangGraph module for medical condition analysis using OpenAI API and Vector DB | N/A | 13 | US2, US5, US6 | High | 4 | - Functionality matches the business requirement for analyzing medical conditions (e.g., prevalence, treatments, research trends). - AI model provides accurate and relevant insights based on the available data. - APIs respond within acceptable latency and return correct status codes. | Unit Tests: Test individual components of the LangChain/LangGraph module.Integration Tests: Verify end-to-end data flow from Vector DB to LangChain/LangGraph and back.API Testing (Backend only): Verify request/response formats, status codes, and error handling.UAT: Confirm AI analysis provides accurate and useful answers to medical condition related queries.
Epic 2: AI-Powered Research Analysis Engine | US8 | Drug Efficacy & Safety Analysis | Backend | Implement AI pipeline for drug efficacy, side effects, and safety profiling | N/A | 13 | US2, US5 | High | 4 | - Functionality matches the business requirement for analyzing drug efficacy and safety profiles. - AI model provides accurate and relevant insights based on the available data. - APIs respond within acceptable latency and return correct status codes. | Unit Tests: Test drug-specific data extraction and analysis.Integration Tests: Verify AI pipeline processes clinical trial and paper data correctly.API Testing (Backend only): Verify request/response formats, status codes, and error handling.UAT: Confirm AI analysis provides accurate and useful answers to drug efficacy and safety queries.
Epic 2: AI-Powered Research Analysis Engine | US9 | Company Growth & Future Areas Analysis | Backend | Develop AI module for analyzing company financial data and market trends | N/A | 8 | US4, US6 | High | 5 | - Functionality matches the business requirement for analyzing company growth and future areas. - AI model provides accurate and relevant insights based on the available data. - APIs respond within acceptable latency and return correct status codes. | Unit Tests: Test financial data parsing and trend identification.Integration Tests: Verify AI module processes financial and media data.API Testing (Backend only): Verify request/response formats, status codes, and error handling.UAT: Confirm AI analysis provides accurate and useful answers to company-related growth and future queries.
Epic 3: Conversational Interface & Reporting | US10 | Implement Conversational Chatbot | Frontend | Build React chatbot interface with real-time interaction | Chat window, message bubbles, input text box, send button, typing indicator, loading states | 5 | US7, US8, US9 | High | 5 | - Functionality matches the business requirement for a conversational chatbot. - Chatbot responds promptly and accurately to user queries. - UI is responsive and consistent with design guidelines. - All UI objects listed are present and functional. | Unit Tests: Test chat message rendering and input handling.Integration Tests: Verify end-to-end flow between frontend chatbot and backend AI services.UI/UX Testing (Frontend only): Verify presence of all UI objects and interactions; test responsiveness on multiple screen sizes.UAT: Confirm chatbot meets user needs and acceptance criteria (e.g., natural language understanding, relevant answers).
Epic 3: Conversational Interface & Reporting | US11 | Display Research Analysis Results | Frontend | Develop dynamic reporting dashboard for AI insights | Search bar, filter options, result cards/tables, charts (bar, line, pie), data export buttons (CSV, PDF), pagination | 8 | US7, US8, US9 | High | 6 | - Functionality matches the business requirement for displaying research analysis results. - Results are presented clearly and concisely. - The UI is responsive and consistent with design guidelines. - All UI objects listed are present and functional. | Unit Tests: Test data rendering in various chart types and tables.Integration Tests: Verify data flow from backend AI services to frontend display.UI/UX Testing (Frontend only): Verify presence of all UI objects and interactions; test responsiveness on multiple screen sizes.UAT: Confirm report display meets user needs and acceptance criteria (e.g., easy to understand, comprehensive).
Epic 3: Conversational Interface & Reporting | US12 | User Authentication & Authorization | Frontend, Backend | Implement user login, registration, and role based access control | Login form, registration form, password reset, user profile, role management UI (for admins) | 5 | - | High | 1 | - Users can securely register and log in. - Role based access control (RBAC) correctly restricts access to features based on user roles. - No security vulnerabilities detected. - UI is responsive and consistent with design guidelines. - All UI objects listed are present and functional. | Unit Tests: Test authentication and authorization logic.Integration Tests: Verify secure communication between frontend and backend.UI/UX Testing (Frontend only): Verify presence of all UI objects and interactions; test responsiveness.API Testing (Backend only): Test authentication tokens, authorization headers.Security Testing: Penetration testing, vulnerability scanning.UAT: Confirm secure and correct user access.
Note on E1: ====== ID#AAABpXG2BCI Sridhar Pai (2025-08-16 10:48:16) Consider date when clinical trials data was extracted for the first time. date when clinical trials data was extracted last time.
Note on C5: ====== ID#AAABpXG2BCM Sridhar Pai (2025-08-16 10:50:56) Form 10-q (Quarterly report) also to be extracted in addition to Form 10-k